## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S2 | S2 | US-001 | Discussion on Dask Libraries, Architecture, and Workflow | MUST HAVE | Dask Documentation | Gogula Avinash Kumar | 3- Completed
S3 | S3 | US-001 | Configuration Management and Understanding How Dask Stores and Manages Data Internally | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S4 | S4 | US-001 | Creating Development Environment, Git Repository Setup, and Virtual Environment Configuration | MUST HAVE | github , vs Code | Gogula Avinash Kumar | 3- Completed
S5 | S5 | US-001 | Project Overview: Problem Statement, Outcomes, Modules, and Dask Cluster Setup | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S6 | S6 | US-001 | Topic Finalization and Project Root Folder Structure Setup | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S7 | S7 | US-001 | Client and Cluster Implementation with Log Data Processing Setup | MUST HAVE | google | Gogula Avinash Kumar | 3- Completed
S8 | S8 | US-001 | Dask Distributed Implementation and LocalCluster Workflow Setup | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S9 | S9 | US-001 | Schema Design Discussion and Implementation | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S10 | S10 | US-001 | Log Processing Pipeline Implementation: Parser, Ingestion, Data Cleaning, Loader, and Anomaly Detection | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S11 | S11 | US-001 | Regex Implementation and Milestone 1 Execution | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S12 | S12 | US-001 | Milestone 1: Review, Evaluation, and Viva Presentation | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S13 | S13 | US-001 | tepping into Milestone 2: Workflow Planning and System Expansion | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S14 | S14 | US-001 | Transition from Sample Logs to Real-Time Data Monitoring | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S15 | S15 | US-001 | Converting Raw Logs to Tabular Structure and Designing the Data Processing Pipeline | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S16 | S16 | US-001 | Pipeline Implementation Through Code and Project File Creation | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S17 | S17 | US-001 | Metadata , Object and DataFrame Implementation Discussion | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S18 | S18 | US-001 | Project Upgrade and Enhancement Implementation | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S19 | S19 | US-001 | Milestone 2 Review and Discussion on Milestone 3 | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S20 | S20 | US-001 | Milestone 3 :Introduction to Anomaly Detection, Z-Score Method, and Types of Anomalies | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S21 | S21 | US-001 | Review of Project ,Presentation and Alerting Mechanisms | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S22 | S22 | US-001 | Implementing Email Alert Module for Log Monitoring System | SHOULD HAVE | google, vs code | Gogula Avinash Kumar | 3- Completed
S23 | S23 | US-001 | Discussion on Email Communication Protocols (SMTP, POP, IMAP) | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 2- In Progress
S24 | S24 | US-001 | Introduction to Mean, Standard Deviation, and Z-Score for Anomaly Detection | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S25 | S25 | US-001 | Using Mean to Identify Normal Patterns in System Logs | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S26 | S26 | US-001 | Detecting Abnormal Events with Z-Score | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S27 | S27 | US-001 | Filtering Error Logs for Effective Anomaly Detection Analysis | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S28 | S28 | US-001 | Implementing Statistical Anomaly Detection in detection.py and email_alert.py | SHOULD HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S29 | S29 | US-001 | Designing the Log → Pipeline → Anomaly Detection → Alert Workflow | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S30 | S30 | US-001 | Modifying main.py to Integrate Log Processing, Detection, and Alerts | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S31 | S31 | US-001 | Log Data Generation using Random Method &File Handling Techniques | MUST HAVE | Google/w3school | Gogula Avinash Kumar | 3- Completed
S32 | S32 | US-001 | Final Integration and System Results | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S33 | S33 | US-001 | Milestone 4: Introduction to Data Visualization and Dashboard Development | MUST HAVE | streamlit.org | Gogula Avinash Kumar | 3- Completed
S34 | S34 | US-001 | Introduction to Data Visualization and Dashboard Tools (Streamlit, Dash, Plotly) | SHOULD HAVE | streamlit.org | Gogula Avinash Kumar | 3- Completed
S35 | S35 | US-001 | Exploration of Plotly for Interactive Data Visualization and Chart Development | SHOULD HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S36 | S36 | US-001 | integration of Streamlit with Backend Pipeline and Dashboard Development | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S37 | S37 | US-001 | Dashboard Enhancement, Project Review, Repository Update, and Presentation Preparation | SHOULD HAVE | github , vs Code | Gogula Avinash Kumar | 3- Completed
Note on F1: ====== ID#AAAB1I0k4O0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 82.5 | 21 | 21 | 17 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Why Do We Use Configuration Files? | 2026-02-02 | 2026-02-05 | saikumar Mudam | Others | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Environment Setup | 2026-02-06 | 2026-02-10 | saikumar Mudam | Design | 3- Completed | 1 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | strip() and Dask bag | 2026-02-13 | 2026-02-14 | saikumar Mudam | others | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Log Schema Finalization | 2026-02-20 | 2026-02-22 | saikumar Mudam | coding | 3- Completed | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Log Processing Pipeline using Dask (Batch) | 2026-02-24 | 2026-02-25 | saikumar Mudam | coding | 3- Completed | 4 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Transition to Real-Time Log Processing Pipeline | 2026-02-26 | 2026-02-28 | saikumar Mudam | Others | 3- Completed | 1 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Parallel Processing and Validation | 2026-03-03 | 2026-03-04 | saikumar Mudam | Others | 3- Completed | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Convert Raw Logs to Structured Dask DataFrame | 2026-03-06 | 2026-03-07 | saikumar Mudam | Design | 3- Completed | 10 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Z-Score Based Anomaly Detection | 2026-03-09 | 2026-03-10 | saikumar Mudam | coding | 3- Completed | 3 | 1 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Email Alert System Implementation | 2026-03-11 | 2026-03-11 | saikumar Mudam | Design | 3- Completed | 4 | 1 | 3 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Explore Dask and Ray | 2026-03-13 | 2026-03-14 | saikumar Mudam | coding | 3- Completed | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | Log Data Generator | 2026-03-16 | 2026-03-17 | saikumar Mudam | coding | 3- Completed | 10 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 13 | Explore Render.com for Deployment | 2026-03-19 | 2026-03-19 | saikumar Mudam | Others | 3- Completed | 1.5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 14 | Streamlit Setup and Basic App | 2026-03-20 | 2026-03-21 | saikumar Mudam | Design | 3- Completed | 13 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 15 | Menu and Menu Bar Design | 2026-03-22 | 2026-03-22 | saikumar Mudam | coding | 3- Completed | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 16 | Integrate Streamlit with Backend Pipeline | 2026-03-23 | 2026-03-23 | saikumar Mudam | coding | 3- Completed | 6 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 17 | Dashboard Development – Line, Bar, Pie, Heatmap (Plotly) | 2026-03-24 | 2026-03-24 | saikumar Mudam | Research | 3- Completed | 8 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 18 | Anomaly Detection, Visualization, Integration | 2026-02-24 | 2026-03-25 | saikumar Mudam | Coding , Testing | 3- Completed | 2 | 1 | 1 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 19 | Repository Update – Add MIT Licence | 2026-03-26 | 2026-03-27 | saikumar Mudam | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABz4P6GCc Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABz4P6GCo Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABz4P6GCs Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABz4P6GCQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABz4P6GCU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB1I0k4Ow Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABz4P6GCw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABz4P6GC0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABz4P6GCg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABz4P6GCM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABz4P6GCY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABz4P6GCk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABz4P6GCI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABz4P6GC4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABz4P6GC8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB1I0k4O4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABz4P6GCE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | 1 | Understanding the role of configuration files in project structure | Studied project architecture and implemented config module for better separation
S2 | 2 | Confusion in Dask concepts (Bag vs DataFrame processing) | Explored Dask documentation and tested sample examples for clarity
S3 | 3 | Difficulty in implementing Z-score calculation for anomaly detection | Revisited statistical concepts and validated implementation using sample data
S4 | 4 | Issue with SMTP email authentication while sending alerts | Configured Gmail App Password and enabled secure connection using starttls()
S5 | 5 | Errors in parsing and structuring raw log data | Debugged parsing logic and ensured correct schema mapping using metadata
S6 | 6 | Difficulty integrating Streamlit with backend pipeline | Refactored code to properly pass processed data into Streamlit dashboard
S7 | 7 | Plotly graphs not displaying correctly due to data format issues | Corrected DataFrame structure and verified visualization logic
S8 | 8 | Challenges in designing dashboard navigation (menu, dropdown, upload) | Implemented Streamlit UI components and structured dashboard layout

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7